## Sheet1
Key Dates | Project Description | 2017-09-28 |  |  | Today's Date | 2017-09-08
| Half-time Crunch | 2017-10-20
| All Content Run-Through | 2017-11-03
| Final Presentations Due | 2017-11-15
| 6 Minute Pitch | 2017-11-17
Phase | Action | Deadline | Expected Outcome | Action Item Owner | Status | Comments
1 - Data Collection | Collection of existing exit interview data | 2017-09-06 | Collection of raw data | Anna | In Process
1 - Data Collection | Collection of data from Corporate interviews | 2017-09-06 | Collection of raw data | Amanda | In Process | Unknown likelihood for successful data collection
1 - Data Collection | Stripping data of employee identification | 2017-09-07 | Data will be stripped of idenfitiable information and a unique ID number assigned that can be paired back to confidential information | Anna / Grace | Not Started
1 - Data Collection | Review of stripped data | 2017-09-08 | General understanding of variables, count of data | All | Not Started
2 - Project Description | Solution Brainstorming | 2017-09-13 | Required for description submission - generate a few ideas based on existing data | All | Not Started
2 - Project Description | Develop project description | 2017-09-19 | 1 page deliveryable in draft format | ? | Not Started
2 - Project Description | Team review of project submission | 2017-09-22 | Mark-ups and edits provided by team | All | Not Started
2 - Project Description | Submission of project description | 2017-09-27 | Goal Met | ? | Not Started
3 - Data Analysis | On-boarding of student researchers | 2017-09-15 | Students understand roles and project description | ? | Not Started
3 - Data Analysis | Format data for analysis and select data processing methodology(ies) | 2017-09-26 | Data is formatted so that it can be processed by selected analytical tool | Alberto/ Amanda/ Students | Not Started | More likely than not, the data won't have to formatted at origin as much as every time we feed it to a new algorithm
3 - Data Analysis | Conduct cross tabulation of data for trending review | 2017-10-02 | Results will allow for trend analysis and deeper research | Alberto / Students | Not Started
3 - Data Analysis | Additional data analysis following cross tabulation results | 2017-10-12 | Additional information or variables that are important for development of final product | Alberto/ Students | Not Started
4 - Product Development | Brainstorming of ideas for final product | 2017-10-16 | List of ideas for group vote | All | Not Started | This is probably an activity to be considered throughout the whole process
4 - Product Development | Selection of final product | 2017-10-18 | Selection of final product for development | All | Not Started
4 - Product Development | Development of final product | 2017-11-03 | Working model of final product (or conceptual designs) | Will depend on type of product | Not Started
5 - Final Presentation | Outline presentation and handouts | 2017-11-01 | Draft of presentation and handouts | ? | Not Started
5 - Final Presentation | Finalize presentation and handouts | 2017-11-14 | Final items needed for sales pitch | ? | Not Started
5 - Final Presentation | Dry-run presentation | 2017-11-15 | Practice of presentation, review areas for improvement, make necessary adjustments for final presentation | ? | Not Started
5 - Final Presentation | Final presentation | 2017-11-17 | Win! | ? | Not Started
Note on B14: A. Miner: The purpose of this challenge is to deliver a real solution to the industry problem that your team has been assigned. Your solution should be well-researched and implementable based on real, existing technology. If your solution relies on technology that does not yet exist, you should have a viable design and detailed explanation for that new technology, if not a proof of concept. Develop a detailed design, implementation and operation strategy. Quantify cash flows associated with the implementation and ongoing operation of your solution, including capital expenditures, its estimated long-term operational cost or savings, and estimated revenues. Explain why your solution is the best solution for this problem, and examine the barriers of entry for competitors who may look to imitate this solution. Provide a detailed write-up of the above information Distill your concept into a 1 to 2 page investor pitch sheet, and a compelling 6-minute presentation. Teams Submit, in one-page, a description of your team challenge and an overview of the solution(s) you plan to investigate. Email to: Mercado, Raquel Raquel.Mercado@Avangrid.com